## Title Slide
(Commodity to Be Reviewed)
Review Description: | (ex: Technical Review #1) | Review Date | Date
Supplier Name
Program(s): | 'Add program name in the Title Slide' (ex: c1lx)
CG5885

## Required Forms to be Submitted
REQUIRED FORMS
Review Description: | (ex: Technical Review #1) (Commodity to Be Reviewed) |  | Review Date | Date
Programs: | 'Add program name in the Title Slide' (ex: c1lx)
GM 1804c - Piece Price Breakdown Form - GDiMPS
GM SMART 1810 - Tooling Breakdown Form - GDiMPS
Capacity and Grouping Form (if applicable)
Supply Chain Cost Break Down Sheet (CBDS) Form
Expendable Packaging Quote
Appendix A - RASIC (signed)
Appendix M - 'SCS' (Supplier Concept Sheet)
Appendix M7 - Technical Issues List
Feasibility Commitment Form (signed)
GM1927-03 - Supplier Quality SOR Form (signed)
GM1927-13 – Technical Review Checklist
GM 1927- 21 GAP Analysis and Severity and Detection Transition Form
IL (International Logistics) Form (as required)

## Technical Review Process
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
SOR Received by Supplier | 1 | [17 empty] | Commercial Issues are not addressed in the M7 Techinal Issues List, they are to be addressed in the 1804c directly.
Technical Reviews Scheduled Tech Rev. Agenda Sent out in Meeting Notice | 1 | [17 empty] | The second technical review should focus on closing out remaining technical issues and Agenda items marked Red / Yellow from the first technical review.
Supplier completes SOR Review and Prepares for Technical Review | 1 | 2 | 3 | 4 | [14 empty] | All Technical Issues should be identified in the first technical review
Technical Review #1 |  |  |  |  | 5 | [13 empty] | Any new technical issues identified in the 2nd tech review should be addressed using the Appendix M7 vs. SOR Appendices Updates.
Team works to resolve identified Technical Issues |  |  |  |  | 5 | 6 | 7
Technical Review #2 | [7 empty] | 8
SOR Finalized | [8 empty] | 9
Technical review Process
Technical Issues
Course to Fine
No New Technical Issues
Post Tech Rev #1

## Technical Review_Attendance
Technical Review Attendance
Review Description: | (ex: Technical Review #1) (Commodity to Be Reviewed) |  |  |  | Review Date | Date
Programs: | 'Add program name in the Title Slide' (ex: c1lx)
Participants on the Phone Email the GM Buyer with the following information: Name, Title, Contact information (phone & email) Participants in the Room Complete the Sign-In Sheet
|  | Present (Yes / No) | Note: Set Autofilter to "All" to see topics that are not Associated with the Peer Review Types Selected.
Name |  | YN | Role | E-mail (Optional) | Phone (Optional) | Comment (Optional)
Buyer - GM Purchasing
Design Release Engineer (DRE) - GM
Lead Technical Engineer (TLE) - GM
Engineering Group Manager (EGM) - GM
Vehicle System Engineer (VSE) - GM
Subsystem Validation Engineer (SVE) - GM
BOM Family Owner (BFO) - GM
People
Finder
Note on B5: Enter Program Name(s)
Note on A9: Short description of the role to be played at the Peer Review.

## Tech Review Agenda
Technical Review Agenda
| Review Description: |  | (ex: Technical Review #1) (Commodity to Be Reviewed) |  |  |  |  | Review Date | Date
| Programs: |  | 'Add program name in the Title Slide' (ex: c1lx)
| Start | End | Duration | Item | Requirement | File Link | Assessment Method | Pass / Fail | Risk | Supplier | Purchasing | Engineering | Supplier Quality | GD & T | Validation | Performance | Cost Engineering | Advanced Manufacturing | Polymers | CAE | PPO | Service | Design
| 8:00 | 8:05 | 0:05 | Welcome & Introductions | [5 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 8:05 | 8:15 | 0:10 | General Motors – Program Review & Updates; Key Objectives | • Appendix B – General Program Description • Key Objectives |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 8:15 | 8:25 | 0:10 | General Motors & Supplier –Timing Charts | • Appendix B – Review timing plan from nomination to service, relative to GM VDP milestones |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk Criteria: GM team assessment Feedback from GM team assessment will be provided post Tech Review 1. |  |  | x | x | x | x | x | x | x |  | x | x | x | x | x | x
| 8:25 | 8:30 | 0:05 | General Motors – RASIC | 1. Appendix A – RASI Mail out item. Must be provided 48 hours prior to Tech Review. Provide signed RASIC |  | PASS / FAIL Evidence: Signed RASIC, or List exceptions and counterproposals as part of M7 response |  |  | x | x | x | x | x | x | x |  | x | x | x | x | x | x
| 8:30 | 8:35 | 0:05 | General Motors & Supplier - New Tech | 1a. New Design, Process, Software or Technology to GM? |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk (If yes is true for any Crietria below) Criteria: New to GM or Supplier Application of Industry Technology but new to GM or Supplier Application of Existing GM Technology but new to the Commodity or Components |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 8:30 | 10:30 | 2:00 | General Motors & Supplier –Bill Of Material Review | 2. Appendix B2 eBOM • EBOM Summary • Appendix F7 – GD&T Requirements • Appendix F10 – Materials • Appendix F5 – Color & Trim • STI (Strategic Tooling Initiative) Expectations - Identical or common? Tooling Concept Sheets - STI and NON STI Supplier responsible • Tool shop Plan (Supplier to identify the toolshop that they will use for each part) • Tooling Concept Sheets Supplier should provide information (minimum 1 slide per GM part number) which demonstrates understanding of technical content, including, at minimum: - Manufacturing Process for assembly - Strategy for Pre-Production manufacturing Process Flow Charts (if different from production), Manufacturing Locations/Material Flow including Material Handling and Logistics) - Tool shop plan (identified by the last review) - Material selection (including "Resin Buy") and manufacturing process for all components - Capitol Equipment (identify New vs. possible reuse opportunities and constraints to be captured in Appendix M7) - Confirm "Make" / "Purchased" / "Directed" for all components - Manufacturing strategy to achieve GD&T requirements (i.e. post-piercing, fixture-set parts through slip planes, etc.) - Description of checking fixtures planned (including "Purchased" and "Directed Buy" components) - All open points requiring GM clarification 3. Appendix B1 – LCRs (Lean Capacity Rates) |  | PASS / FAIL Criteria: GM team assessment Feedback from GM team assessment will be provided post Tech Review 1. Evidence for Manufacturing Process: Preliminary Process Flow provided, including (but not limited to): - Error proofing and / or verification stations with rationale - End of Line / Functional Testing (including electrical) and GP12 - New manufacturing technologies and resulting training requirements - Critical / safety critical stations and resulting training requirements - Demonstration of compliance to SOR traceability requirements - Support of Pre-Production Materials if different than Prodution |  |  | x | x | x | x | x | x | x | x | x | x | x |  |  | x
| 10:30 | 10:35 | 0:05 | Supplier - Resin Buy Program | Confirm understanding of the "Directed Buy" & "Purchased Items" process, including any mechanims. Provide specific examples from existing GM programs |  | PASS / FAIL Criteria: List provided |  |  | x | x | x | x |  | x | x | x |  | x |  |  |  | x
| 10:35 | 10:40 | 0:05 | Supplier - Directed and Purchased items | Confirm understanding of the "Directed Buy" & "Purchased Items" process. Provide specific examples from existing GM programs |  | PASS / FAIL Criteria: List provided |  |  | x | x | x | x |  | x | x | x |  | x |  |  |  | x
| 10:40 | 10:50 | 0:10 | Supplier - eGD&T | (1) Does supplier capability align with dimensional requirements ( Datum Strategy, Tolerances) specified in the preliminary drawing found in the 'F7' Tab inside 'Appendix B2' of the eSOR? (2) Has the supplier submitted an M7 highlighting any concerns in meeting the template drawing dimensional requirements and are the actions/agreements documented? (3) Has the supplier reviewed the Mentor-287 content? Do they have any questions (see link in appendix B2, F7 tab)? (4) Does supplier's designated GD&T person have experience with ASME Y 14.5- 2009 / 2018? (5) Is the supplier capable of completing GD&T stack studies to determine hole sizes and clearances needed? (for SI3 only) (6) Does the supplier have a designated GD&T person to work on this program and what is their job title and contact information? (for SI3 only) 'Mail out item. Must be provided 48 hours prior to Tech Review. | Link to Mentor-287 | PASS / FAIL Evidence: (1) Yes/No (2) Yes/No (3) Yes/No (4) Yes/No (5) Yes/No (6) Name & Designation |  |  | x | x | x | x | x | x | x |  | x | x |  | x
| 10:50 | 11:00 | 0:10 | Supplier - Tunable Features | Confirm understanding that tooling iteration(s) of tunable features will be executed at no cost to GM Review and agree plan to execute tunable features (i.e. burn to nominal vs "steel safe") |  | PASS / FAIL Evidence: Supplier agreement or Plan Provided, or Exceptions listed in M7 response |  |  | x | x | x | x | x | x | x | x | x | x | x |  |  | x
| 11:00 | 11:30 | 0:30 | Lunch
| 11:30 | 11:50 | 0:20 | Supplier - Appendix E8 | '4. Appendix E8 – Polymer Engineering Support Manufacturing Engineering Statement of Requirements 'Mail out item. Must be provided 48 hours prior to Tech Review. Review proposed E8 parts based on eSOR; understands mold flow requirements |  | PASS / FAIL Evidence: Signed agreed list of E8 Parts and mold flow requirements, or Exceptions listed in M7 response |  |  | x | x | x | x |  | x | x | x |  |  | x
| 11:50 | 12:05 | 0:15 | Supplier - ADV Plan | '5. Appendix G2 – Analysis Development Validation Process Tasks & Deliverables 'Mail out item. Must be provided 48 hours prior to Tech Review. Review proposed ADV Plan based on eSOR VCRI |  | PASS / FAIL Evidence: Signed ADV Plan, or Exceptions listed in M7 response |  |  | x | x | x | x |  | x | x | x |  |  | x
| 12:05 | 12:10 | 0:05 | Supplier - Sub System Technical Specification Documents (SSTS) | 6. SSTS - Appendix C1 / C2 GMW1927-3 – Supplier Quality General Requirements o PQC Requirements – where a PQC is identified a CpK ≥ 1.67 is required. |  | PASS / FAIL Evidence: Signed documents, or Exceptions / Plan to close gaps listed in M7 response |  |  | x | x | x | x |  | x | x |  |  |  |  | x
| 12:10 | 12:15 | 0:05 | Supplier - CCC China Compolsory Certification | Confirm agreement to achieve certification for all parts. Confirm understanding of the CCC process. Provide specific examples from existing GM programs. |  | PASS / FAIL Criteria: Agreement to achieve certification for all parts List provided |  |  | x | x | x | x |  | x | x | x
| 12:15 | 12:30 | 0:15 | Break
| 12:30 | 12:35 | 0:05 | Supplier - General Company Information | Mail out item. Must be provided 48 hours prior to Tech Review. Provide an organization overview Commercial Overview of Company -Corporate structure & divisions -History, products, locations -Market coverage & product mix -What percentage is GM of total sales? -Future plans Organizational Capabilities -Program management and change management system -Summarize the key technology, concept, or strategy on which your business is based. Show similar products currently producing. Technical Capabilities -Unigraphics Compliance and data communication process between GM, your company and Tier II suppliers -Product Design Capabilities -Product Development Tools -Prototype Capabilities -APQP Product Development Process -Functional and Developmental Testing Safety -Major OSHA/safety violations last 5 years -Work related accidents within last 5 years Continuous Improvements -Investment in production technology and equipment as a % of sales last year -Change in man hours per ton by year for the last 5 years |  | N/A - Provided for information only, not to be discussed at Tech Review unless requested (Note: adjust time allocated if review is requested) |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 12:35 | 12:50 | 0:15 | Supplier - Organizational Information | 1.1. Provide an organization chart identifying required resources to successfully execute the program, including: - Names - Responsibilities - Geographical location - Experience, including number of new program launches - Percentage dedicated to program, including start and end timing related to GP-12 (GM1920) exit If positions are not yet filled, review the on-bording plan relative to source and launch timing |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk Risk Items: Past experience with similar / same components Time in company etc. Knowledge of GM systems (TCAE, CEMENT, Supplier Power etc.) Previous experience with GM VDP Geographic distance from VEC Timezone difference from VEC Resource allocation (empty org slots etc.) |  |  | x | x | x | x | x | x | x |  | x | x | x | x | x | x
| 12:50 | 12:55 | 0:05 | Supplier -Facilities | Mail out item. Must be provided 48 hours prior to Tech Review. 1.2. Provide ISO/TS16949 & BIQs certification and expiration date • Location of proposed DUNs. New to Country or Region? • Experience with supplying to GM and/or other OEMs. New to GM? |  | PASS / FAIL Existing DUNS - Pass / Fail (GM requirement to be ISO/TS16949 & BIQs compliant prior to nomination) Greenfield / Brownfield - Demonstrated plan to be ISO/TS16949 & BIQs compliant 6 months post SORP Evidence: 1 page summary of compliance
| 12:55 | 13:05 | 0:10 | Supplier -Facilities | 1.3. Demonstrate quoted DUNS's experience with: Experience in similar type programs, including Engineering responsibility and production volumes - Similar GM product - Other GM product - Other OEM similar product |  | 'Risk Assessment Risk = 0 - Demonstrated success with similar GM product Risk = 1 - Demonstrated success with other GM product Risk = 2 - Demonstrated success with other OEM product Risk = 3 - No experience |  |  | x | x | x | x |  |  |  | x | x | x
| 13:05 | 13:15 | 0:10 | Supplier -Facilities | 1.4. Manufacturing plan for this program • Proposed Manufacturing location(s) and process capabilities • Manufacturing location process capabilities • Capacity planning; facility and capital equipment requirements • Technology transfer plans • Tier 2 plans (partnerships, equal partners, joint ventures, etc) • Manufacturing location (at country level) and material flow for all subcomponents |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk Risk items: No plant footprint provided Balance of existing / proposed programs Utilization > 90% - according to R@R docs Lack of contingency plan Hiring history and retention of operators |  |  | x | x | x | x |  |  |  | x | x | x
| 13:15 | 13:20 | 0:05 | Supplier -Facilities (Greenfield/Brownfield) | 1.5 “Brick and mortar” requirements: For all new manufacturing facilities (Greenfield or Brownfield) OR capacity expansions of an exisiting facility (increase square footage) Mail out item. Must be provided 48 hours prior to Tech Review. Provide completed Tech Review Tab of GM1927-31 (Greenfield / Brownfield Assessment Form) |  | PASS / FAIL Evidence: Completed GM1927-31 |  |  | x | x | x | x |  |  |  |  | x | x
| 13:20 | 13:25 | 0:05 | Supplier - Facilities | List all expedited shipping requiring GM Tactical Operations intervention for the prior 12 months |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk Risk items: Number of occurances and rationale Number of yard holds / lost units etc.
| 13:25 | 13:30 | 0:05 | General Motors & Supplier - Sourceability Report Review | Review the current Sourceability Report status of the quoted manufacturing DUNS. If Red, provide explanation of the current status and corrective actions to meet the Sourceability Report requirements. |  | PASS/FAIL Evidence: A Robust plan to be green on the bidlist
| 13:30 | 13:35 | 0:05 | General Motors & Supplier - Capability SQ Team Feasibility | Mail out item. Must be provided 48 hours prior to Tech Review. Review SQ Team Feasibility Commitment letter to confirm supplier capability or exceptions |  | PASS / FAIL Criteria: Supplier Signed SQFC provided. Additionally, per SQFC, for "NO" items: All "no" answers are supported with attached comments identifying concerns and/or product changes to enable the organization to meet the specified requirements. |  |  | x | x | x | x | x | x | x |  | x | x |  | x
| 13:35 | 13:40 | 0:05 | Supplier - Quality Improvement Plans & Lessons Learned | Provide PRR and IPB glide paths and paretos (both Corporate & quoted DUNS) over time Describe process to implement lessons learned from PRRs and IPB (both Corporate & quoted DUNS) |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk Risk Items: - Number, type and severity of PRRs - Shape of PRR and IPB glide path - Evaluation of corrective action process |  |  | x | x | x | x |  | x | x
| 13:40 | 13:45 | 0:05 | Supplier - Warranty and Quality Improvement Plans | Provide IPTV and CPV glide paths and paretos (both Corporate & quoted DUNS) over time Describe process to implement lessons learned from IPTV and CPV (both Corporate & quoted DUNS) |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk Risk Items: - IPTV & CPV - Evaluation of corrective action process |  |  | x | x | x | x |  | x | x
| 13:45 | 14:00 | 0:15 | Break
| 14:00 | 14:15 | 0:15 | General Motors & Supplier - Exceptions and improvements | Mail out item. Must be provided 48 hours prior to Tech Review. Review supplier provided Appendix M7 |  | PASS / FAIL Evidence: Team agreement to exception as listed, or Team agreement to modified exception, or GM rejection of exception (requires supplier to re-review and counterpropose) |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 14:15 | 14:30 | 0:15 | General Motors & Supplier - Exceptions and improvements | Mail out item. Must be provided 48 hours prior to Tech Review. Review supplier technology or optimisation ideas / Engineered solutions that can be implemented Demonstrate that new technology enables all eSOR requirements (i.e. post processing or painting does not impact GD&T, validation requirements are met) |  | PASS / FAIL Evidence: Team agreement to optimisation as listed, Team agreement to modified optimisation, or GM rejection of optimisation |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 14:30 | 14:40 | 0:10 | General Motors & Supplier - Exceptions for quotation of program | 7. 1804 / 1810 Forms – Requirements • Transparency • Cost Model Agreement • Provide Details |  | PASS / FAIL Evidence: Team agreement , or rejection |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 14:40 | 14:50 | 0:10 | General Motors & Supplier - Exceptions for forming or welding Program Execution | 8. Forming or Welding • Program Expectations • Tooling Cadence • IVER Expectations (parts representative from production process) • CVIS definition w/boundary samples • First Time Quality (Home line & production crew readiness) • PPAP & Run at Rate |  | PASS / FAIL Evidence: Team agreement , or rejection |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 14:50 | 15:00 | 0:10 | General Motors & Supplier - Exceptions for sourcing and check in | 9. Sourcing Timing Requirements and Check In Requirements |  | PASS / FAIL Evidence: Team agreement , or rejection |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 15:00 | 15:05 | 0:05 | SI 3 ONLY: DFMEA | Demonstrate how lessons learned are captured within the DFMEA |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk |  |  | x | x | x | x | x | x | x | x |  | x | x |  |  | x
| 15:05 | 15:20 | 0:15 | SI 3 ONLY: Preliminary PFMEA | Provide a preliminary / baseline PFMEA that meets the requirements of BIQS elements 3 & 4 for quoted DUNS. - Provide PFMEA that includes all operations within the plant, including labeling and handling. - Provide PFMEA that consistently and correctly applies severity, occurrence and detections values from the approved ranking tables - Provide PFMEA in a format that includes product requirements, multiple causes for failure modes where applicable and severity is studied based on all risks such as plant risk, customer risk, and end user risk - Provide description of process for reporting and approving PFMEA countermeasures/corrective action, including plant manager role. Identify members of the cross-functional team that create PFMEAs and participate in workshops, reverse PFMEA floor walks, continuous improvement and risk reduction - Identify how high risk items are prioritized (risk limiting method or equivalent) and frequency of cross functional risk reduction reviews that focus on preventing defect from leaving the workstation. (monthly) - Identify how PFMEA changes flow into Process Control Plans & Work Instructions |  | Risk Assessment Risk = 0 - Green status to BIQS elements 3 & 4 Risk = 1 - Yellow status to BIQS elements 3 & 4 with timed plans for closure Risk = 2 - Yellow status to BIQS elements 3 & 4 with inadequate plan for closure Risk = 3 - Red status to BIQS elements 3 & 4 |  |  | x | x | x | x |  | x | x |  | x
| 15:20 | 15:30 | 0:10 | SI 3 ONLY: DFMEA/PFMEA Gap Analysis | Provide a completed GM1927-21 DFMEA to PFMEA Gap Analysis for all supplier related line items. DFMEA severities of 10, 9, 8, & 7 are mandatory. - Identify any failure modes that do not meet the required detection and provide an action plan to meet the required detection - Identify any failure modes on the M7 that do not meet the required detection and there is no plan to achieve the required detections. Include counterproposals and completed “ Transition Form” (part of GM1927-21). |  | PASS / FAIL Evidence: Completed "GM1927-21 DFMEA to PFMEA Gap Analysis" For all gaps, agree either: (a) plan to meet the required DET, or (b) exception documented in M7 response |  |  | x | x | x | x |  | x | x |  | x
| 15:30 | 15:35 | 0:05 | SI 3 ONLY: Preliminary Process Control plan | Mail out item. Must be provided 48 hours prior to Tech Review. Provide a preliminary / baseline Process Control Plan |  | PASS / FAIL Evidence: Preliminary Process Control Plan provided, including (but not limited to): - Evidence of PFMEA and LAT connectivity - Control methods and frequency aligned with PFMEA DET rankings |  |  | x | x | x | x |  | x | x |  | x
| 15:05 | 15:10 | 0:05 | SI 3 ONLY: Familiarity with GM Processes | Demonstrate familiarity with GM processes (Pre-Production and Production) and systems. Reference previous programs as required. |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk Risk items: Experience with GM processes such as PPO Process, E-squared, PRTS, CEMENT, TeamCenter etc. |  |  | x | x | x | x | x | x | x | x |  | x | x |  |  | x
| 15:10 | 15:15 | 0:05 | SI 3 ONLY: Engineering Resources (ED&D) | Review resource over time (ED&D) mountain chart, relative to GM VDP milestones |  | Risk Assessment Risk = 0 - No risk Risk = 1 - Low risk Risk = 2 - Medium risk Risk = 3 - High risk |  |  | x | x | x |  |  |  |  | x
[7 empty] | Sum (Pass) = | 0
[7 empty] | Sum (Fail) = | 0
[7 empty] | Status (Must be GREEN to proceed) = | Need Red or green here
[8 empty] | Sum (Risk 0) = | 0
[8 empty] | Sum (Risk 1) = | 0
[8 empty] | Sum (Risk 2) = | 0 |  | All ORANGE items to be reviewed at ECT
[8 empty] | Sum (Risk 3) = | 0 |  | All RED items to be reviewed at ECT
Note on D5: Enter Program Name(s)
Note on B8: Add meeting start time here
Note on D8: Add duration in 0:15 format Exisiting are suggested only

## Technical Issues
Technical Review Issues
Review Description: |  | (ex: Technical Review #1) (Commodity to Be Reviewed) |  |  |  | Review Date | Date
Programs: |  | 'Add program name in the Title Slide' (ex: c1lx)
| Paragraph # | Exception / Assumption / Issue / Clarification | Date Initiated | Response | Target Due Date | (X) When Closed | Date closed | GM Initial | Supplier Initial
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Note on C5: Enter Program Name(s)

## Sample
Z2xx Technical Issues - XYZ Automotive
| Paragraph # | Exception / Assumption / Issue / Clarification | Date Initiated | Response | Target Due Date | (X) When Closed | Date closed | GM Initial | Supplier Initial
1 | App. B, Sec. 2.3(b) content matrix | Carrier: Quoted one pc. SOR did not state 2 pc option. | 2012-03-13 | 3/13/12 Supplier correct assumption. | 2012-03-13 | X
2 | App. B, Sec. 2.4 (b) | A/R Foam (Not clear on thickness) Quoted 6mm foam. | 2012-04-10 | 3/13/12 GM to change SOR/Math from 6mm to 8mm foam. 4/10/12 Updated quote to reflex change | 2012-04-13 | X
3 | App. B, Sec. 2.13.2.2 2.13.2.2.1 | Combine both Upper Belt Down Turned Flange and Belt Line Reinforcement | 2012-05-13 | 3/13/12 GM to provided updated math 21APR12 No information received. 23APR12 Updated Math 24 Error Found. 24APR12 Updated Math 13May12 Supplier received and understands specifications and will comply. | 2012-05-15 | X
4 | Level Setting 7-10-12 |  |  |  |  | X
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## Revision Log
Revision Log
Revision | Date | Comments | Approver
1 | 2019-08-16 | Initial upload of document to GDM | Wayne Witkop
1.1 | 2022-10-26 | GD&T questions updated | Wayne Witkop
1.2 | 2022-11-03 | Link to documents column added | Wayne Witkop