## T1UXF-2 SWB CHV-GMC Matrix
Appendix E10 Bodyshop Material Requirements
[15 empty] | (2028) T1UXF-2 Chevy & GMC SWB - TIMING MILESTONES SORP (1/10/28) - (Arlington Assembly Plant) | [53 empty] | SORP |  |  | 2028-01-10 | [41 empty] | SORP Input: | 2028-01-10
|  |  | Core Panels & Asms | [110 empty] | Do Not DELETE
| T1-UXF-2 Chevy & GMC SWB |  | Template Reference: GVDP 5.7 Major Program Framework
[6 empty] | MRD PTB-C (PPO)(Estimated QTY's) | [8 empty] | MRD PTB-M (PPO) | [8 empty] | MRD Matching (Arlington) | [17 empty] | MRD APPV (Arlington) | [17 empty] | MRD PPV (Arlington) | [17 empty] | MRD NS1 (Arlingtin) | [17 empty] | MRD NS2 (Arlington)
|  |  | Mini-Match |  |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC
| Program Milestone |  | Review |  |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty
| CVER RELEASED PARTS Including SVER/IVER assemblies listed below: Upper Tie Bar Asm FBHP Inner Asm Rocker Inner Asm Plenum Upper Asm Rear W/House Asm Rear End Panel Asm (SUV's Only) Front Impact Beam |  | Week | -107 | M | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 30 | S | 15 | S | 15 | S | Week | -69 | P | 70 | S | 35 | S | 35 | S | Week | -65 | P | 40 | S | 20 | S | 20 | S | Week | -59 | P | 80 | S | 40 | S | 40 | S | Week | -56 | P | 60 | S | 30 | S | 30 | S | Week | -49 | P | 110 | S | 55 | S | 55 | S | Week | -46 | P | 90 | S | 45 | S | 45 | S | Week | -32 | P | 100 | S | 50 | S | 50 | S | Week | -29 | P | 90 | S | 45 | S | 45 | S | Week | -26 | P | 100 | S | 50 | S | 50 | S | Week | -23 | P | 90 | S | 45 | S | 45 | S
|  |  | 2025-12-19 |  |  | 2026-01-09 | [8 empty] | 2026-07-24 | [8 empty] | 2026-09-11 | [8 empty] | 2026-10-09 | [8 empty] | 2026-11-20 | [8 empty] | 2026-12-11 | [8 empty] | 2027-01-29 | [8 empty] | 2027-02-19 | [8 empty] | 2027-05-28 | [8 empty] | 2027-06-18 | [8 empty] | 2027-07-09 | [8 empty] | 2027-07-30
| SVER RELEASED PARTS Except for asm's listed below are shipped to CVER timing: Upper Tie Bar Asm FBHP Inner Asm Rocker Inner Asm Plenum Upper Asm Rear W/House Asm Rear End Panel Asm (SUV's Only) |  | WeekM | -107 | M | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 30 | S | 15 | S | 15 | S | Week | -66 | P | 70 | S | 35 | S | 35 | S | Week | -63 | P | 40 | S | 20 | S | 20 | S | Week | -59 | P | 80 | S | 40 | S | 40 | S | Week | -56 | P | 60 | S | 30 | S | 30 | S | Week | -49 | P | 110 | S | 55 | S | 55 | S | Week | -46 | P | 90 | S | 45 | S | 45 | S | Week | -32 | P | 100 | S | 50 | S | 50 | S | Week | -29 | P | 90 | S | 45 | S | 45 | S | Week | -26 | P | 100 | S | 50 | S | 50 | S | Week | -23 | P | 90 | S | 45 | S | 45 | S
|  |  | 2025-12-19 |  |  | 2026-01-09 | [8 empty] | 2026-07-24 | [8 empty] | 2026-10-02 | [8 empty] | 2026-10-23 | [8 empty] | 2026-11-20 | [8 empty] | 2026-12-11 | [8 empty] | 2027-01-29 | [8 empty] | 2027-02-19 | [8 empty] | 2027-05-28 | [8 empty] | 2027-06-18 | [8 empty] | 2027-07-09 | [8 empty] | 2027-07-30
| IVER RELEASED PARTS Except for asm listed below is shipped to CVER timing: Front Impact Beam | * All IVER * (Except Closures) (Except Fenders) (Except Closure OUTERs) | Week | -107 | M | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 30 | S | 15 | S | 15 | S | Week | -63 | P | 70 | S | 35 | S | 35 | S | Week | -60 | P | 40 | S | 20 | S | 20 | S | Week | -59 | P | 80 | S | 40 | S | 40 | S | Week | -56 | P | 60 | S | 30 | S | 30 | S | Week | -49 | P | 110 | S | 55 | S | 55 | S | Week | -46 | P | 90 | S | 45 | S | 45 | S | Week | -32 | P | 100 | S | 50 | S | 50 | S | Week | -29 | P | 90 | S | 45 | S | 45 | S | Week | -26 | P | 100 | S | 50 | S | 50 | S | Week | -23 | P | 90 | S | 45 | S | 45 | S
|  |  | 2025-12-19 |  |  | 2026-01-09 | [8 empty] | 2026-07-24 | [8 empty] | 2026-10-23 | [8 empty] | 2026-11-13 | [8 empty] | 2026-11-20 | [8 empty] | 2026-12-11 | [8 empty] | 2027-01-29 | [8 empty] | 2027-02-19 | [8 empty] | 2027-05-28 | [8 empty] | 2027-06-18 | [8 empty] | 2027-07-09 | [8 empty] | 2027-07-30
|  | * CLOSURES * Doors & Liftgates (NOT Including OUTERs) (NOT Including Fenders) | Week | -107 | M | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 40 | S | 25 | S | 25 | S | Week | -68 | P | 80 | S | 40 | S | 40 | S | Week | -65 | P | 50 | S | 25 | S | 25 | S | Week | -62 | P | 120 | S | 60 | S | 60 | S | Week | -59 | P | 100 | S | 50 | S | 50 | S | Week | -52 | P | 130 | S | 65 | S | 65 | S | Week | -49 | P | 110 | S | 55 | S | 55 | S | Week | -35 | P | 110 | S | 55 | S | 55 | S | Week | -32 | P | 100 | S | 50 | S | 50 | S | Week | -29 | P | 110 | S | 55 | S | 55 | S | Week | -26 | P | 100 | S | 50 | S | 50 | S
|  |  | 2025-12-19 |  |  | 2026-01-09 | [8 empty] | 2026-07-24 | [8 empty] | 2026-09-18 | [8 empty] | 2026-10-09 | [8 empty] | 2026-10-30 | [8 empty] | 2026-11-20 | [8 empty] | 2027-01-08 | [8 empty] | 2027-01-29 | [8 empty] | 2027-05-07 | [8 empty] | 2027-05-28 | [8 empty] | 2027-06-18 | [8 empty] | 2027-07-09
|  | * CLOSURES * (Fenders Only) | N/A |  |  | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 40 | S | 25 | S | 25 | S | N/A | [8 empty] | Week | -58 | P | 50 | S | 25 | S | 25 | S | N/A | [8 empty] | Week | -52 | P | 100 | S | 50 | S | 50 | S | N/A | [8 empty] | Week | -46 | P | 90 | S | 45 | S | 45 | S | N/A | [8 empty] | Week | -29 | P | 90 | S | 45 | S | 45 | S | N/A | [8 empty] | Week | -23 | P | 90 | S | 45 | S | 45 | S
[6 empty] | 2026-01-09 | [8 empty] | 2026-07-24 | [17 empty] | 2026-11-27 | [17 empty] | 2027-01-08 | [17 empty] | 2027-02-19 | [17 empty] | 2027-06-18 | [17 empty] | 2027-07-30
|  | * CLOSURES* (OUTER Panels Only) | N/A |  |  | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 50 | S | 30 | S | 30 | S | [9 empty] | Week | -65 | P | 70 | S | 35 | S | 35 | S | [9 empty] | Week | -59 | P | 120 | S | 60 | S | 60 | S | [9 empty] | Week | -49 | P | 130 | S | 65 | S | 65 | S | [9 empty] | Week | -32 | P | 110 | S | 55 | S | 55 | S | [9 empty] | Week | -26 | P | 110 | S | 55 | S | 55 | S
[6 empty] | 2026-01-09 | [8 empty] | 2026-07-24 | [17 empty] | 2026-10-09 | [17 empty] | 2026-11-20 | [17 empty] | 2027-01-29 | [17 empty] | 2027-05-28 | [17 empty] | 2027-07-09
| PTB-C, Tool Try Out, PTB-M |  | Ordered Through PPO System | [29 empty] | N/A
| APPV - Body |  | N/A | [29 empty] | U
| PPV - Body |  | N/A | [29 empty] | U
| MVB NS - Body |  | N/A | [29 empty] | U
| MVB S - Body |  | N/A | [29 empty] | U
| MRD S1.0 |  | N/A | [29 empty] | U
PROGRAM SPECIFIC NOTES:
COMMENTS FOR THE ABOVE TABLE:
Parts delivered to the GM Production Plant/GM facility will be at the contracted production piece price. The supplier is responsible for all shipping costs associated to meet the SOR's MRD dates and quantities at the specified quality level.
+ | Quantity is the same for all body parts ordered through MGO (CVER, SVER, IVER) (Exception is the IVER Closures, quantities are higher)
P | The MRD (Begin) date denotes the start date when the specified total Quantity of parts is required. Additional parts may be requested if part quality improvement is needed. The submission of the specified total Quantity may be all at once at the specified MRD (Begin) date if the part quality is met (per direction of the program Matching Team). Otherwise the submissions will be spread over the specified MRD (Begin) date to the specified MRD (End) Date with part quality improving over subsequent submissions. The exact timing of each submission and the quantity for each submission will be communicated to the supplier (per direction of the Program Matching Team). Note: the MRD (Begin) and part Quantity are program specific and will be managed/determined per direction of the Program Matching Team). Note: the order for the total quantity of a part or assembly number should be placed in the system only once per MRD. If parts are to have multiple deliveries, the quantity and frequency of the deliveries/submissions will be managed through direct communications between the Matching Team and the supplier.
S | Additional pieces and/or rework may be needed if a part quality improvement is required. These additional reworks and/or quantities need to be provided at the supplier's expense.
U | For sheet metal parts supplied by Stamping, the material is already comprehended in the Body Shop Validation Category above. The MRD denotes the required date for Carryover Purchased Part Assembly Plant/New Purchased Part/etc (See the FMA Orders & Tracking Responsibility Table from PI).
M | Mini-Match Review is for critical stampings and assemblies. This will include all 12 Critical Sub Assemblies: Front Rail Asm R/L, Rear Rail Asm R/L, Front W/H Asm R/L, Rear W/H Asm R/L, Upper Tie Bar Asm, SUV D-Pillar Asm R/L, and SUV Rear End Panel as well as others to be specified by the Matching Team. Requirements are listed in GM 10067. Objective is to review parts on checking fixture and in production tools in order to understand issues and drive resolution prior to MRD Matching.
Z | POA = Part Of Assembly: The MRD date when parts are required at a Tier 2 supplier in order to support the "Direct Ship" MRD dates with assemblies. Example #1: A GM Metal Center is a Tier 2 supplier of stamped components to an outside, Tier 1, supplier. Parts from the GM Metal Center, Tier2, are due to the Supplier, Tier 1, on the "POA" date to allow sufficient time for the Tier 1 to build assemblies and deliver to the assembly plant on the "Direct Ship" MRD. Example #2: A GM Metal Center and/or an outside supplier are Tier 2 to a Tier 1, Parma or Flint Metal Center. Parts are due to Parma or Flint Metal Center on the "POA" date to allow sufficient time for the Tier 1, Parma or Flint Metal Center, to build assemblies and deliver to the assembly plant on the "Direct Ship" MRD.
D | Directed Buy Parts require a 10% quantity increase over stated MRD quantity, and are required at the Tier 1 supplier a minimum of 2 (two) weeks prior to the MRD date. Any cost associated with adding more than a 10% quantity are the resposibility of the Tier 1 supplier.
T | Consumption of the MRD metal should be planned as MRD +10 days. There are 10 days allocated to receiving, relocating, and reworking material as necessary.
MINIMUM BIW PART SUBMISSION REQUIREMENTS*
| MRD | Tool Level 9 |  |  |  |  | Quality Level *
| PTB-C, Tool Try out, PTB-M and MRD Matching | Production Intent Tooling - At a minimum: Parts formed, trimmed and pierced off production dies. Assemblies must be off certified GEO tools, Manual Teach robotic welds or production hard guns, Production clamps (May be manually actuated), Production weld and clamping sequence must be followed. Checking fixture should be complete and certified. CMM programs written and complete. Sealer,adhesive and studs may be manually applied with templates. |  |  |  |  | Parts to be reviewed by joint Matching Team and Supplier. Supplier to provide data and action plans to meet MRD Matching requirements.
| MRD APPV | Same as Matching * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  |  | Parts to meet requirements defined in GM10067
| MRD PPV | Same as MRD Matching at a minimum * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MRD NS1.0 | Full Production Tooling- Not necessarily at rate, but fully Automatic and at Homeline location - both for dies and assembly tooling. * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MRD NS2.0 | Full Production Tooling- Not necessarily at rate, but fully Automatic and at Homeline location - both for dies and assembly tooling. * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MVB Saleable | * 100% FULL PPAP Required * (Submit documentation 4 weeks prior to MRD or 2 weeks prior to "PPAP" gate date, whichever comes first) |  |  |  |  | Interim PPAP Salable
* | SUPPLIER REQUIREMETS FOR PART SUBMISSION:
1 | The goal is to build a "Nominal Body" and every part is a "Matching" part
2 | Submit 100% production-tooled parts (no laser trim/cutting, etc.). Any non-production intent processes used to manufacture a submitted part must be communicated & reviewed by the Iterative Matching Team.
3 | Drive part to nominal. If part is not at nominal, communicate where it is off nominal. The supplier must possess knowledge of the quality level of the part, and have data, roadmaps, and process capability studies readily available to determine the quality level of the part and to help resolve build issues.
4 | Provide production parts at the initial submittal date and continue to improve the part (drive part to nominal) to resolve build issues PPAP Status required for Non Saleable and Saleable MRD material prior to shipping. Documentation must be submitted 4 weeks prior to MRD.
5 | Work closely with the Iterative Matching Team led by the VDQM, Vehicle Dimensional Quality Manager to resolve part/build issues
6 | Provide improved parts (when part issues are identified & communicated) in a timely manner, per the Iterative Part Submission process.
7 | Work to the latest part GD&T (datums & tolerances). Parts should be measured using the datum strategy communicated in the GD&T. All critical points are to be driven to nominal.
8 | Work closely with the Matching Team and apply your best efforts to improve part quality and provide a part which will ultimately result in a high quality BIW and a finished vehicle with world-class fit and finish.
9 | Any deviations from the required Tool Level at each MRD must be approved by the Matching Team which includes Supplier Quality, Product Interface, BIW Quality Lead, VDQM, and MP Engineers.
10 | PPAP Status required for Non Saleable and Saleable MRD material prior to shipping. See "MINIMUM BIW PART SUBMISSION REQUIREMENTS*" chart above for specific MRD Documentation submittal requirements.
IN SUMMARY:
a. | Every part is a "Matching" part
b. | The goal of the Iterative Matching process is to build a "Nominal Body"
c. | Your tools have to be done by start of Iterative Matching
d. | Be ready to ship Production-Tooled Parts by start of Iterative Matching
e. | Drive your part (s) and assembly (ies) to nominal
f. | Know your issues with the part (s)
g. | Know the Iterative Matching Team and its Leader
h. | Work with the Team to resolve part/asm build issues
i. | Be there with the Team to resolve part/asm build issues
j. | Be ready to provide data as needed

## T1YXF-2 LWB Chevy - GMC
Appendix E10 Bodyshop Material Requirements
[15 empty] | (2028) T1YXF-2 Chevy & GMC LWB - TIMING MILESTONES SORP (1/10/28) - (Arlington Assembly Plant) | [53 empty] | SORP |  |  | 2028-01-10 | [41 empty] | SORP Input: | 2028-01-10
|  |  | Core Panels & Asms | [110 empty] | Do Not DELETE
| T1YXF-2 Chevy & GMC LWB |  | Template Reference: GVDP 5.7 Major Program Framework
[6 empty] | MRD PTB-C (PPO)(Estimated QTY's) | [8 empty] | MRD PTB-M (PPO) | [8 empty] | MRD Matching (Arlington) | [17 empty] | MRD APPV (Arlington) | [17 empty] | MRD PPV (Arlington) | [17 empty] | MRD NS1 (Arlingtin) | [17 empty] | MRD NS2 (Arlington)
|  |  | Mini-Match |  |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC |  | POA Z T |  |  | Common |  | Chevy |  | GMC |  | Direct Ship T |  |  | Common |  | Chevy |  | GMC
| Program Milestone |  | Review |  |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty |  | (Begin)P |  |  | Qty |  | Qty |  | Qty
| CVER RELEASED PARTS Including SVER/IVER assemblies listed below: Upper Tie Bar Asm FBHP Inner Asm Rocker Inner Asm Plenum Upper Asm Rear W/House Asm Rear End Panel Asm (SUV's Only) Front Impact Beam |  | Week | -107 | M | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 30 | S | 15 | S | 15 | S | Week | -69 | P | 70 | S | 35 | S | 35 | S | Week | -65 | P | 40 | S | 20 | S | 20 | S | Week | -59 | P | 80 | S | 40 | S | 40 | S | Week | -56 | P | 60 | S | 30 | S | 30 | S | Week | -49 | P | 110 | S | 55 | S | 55 | S | Week | -46 | P | 90 | S | 45 | S | 45 | S | Week | -32 | P | 100 | S | 50 | S | 50 | S | Week | -29 | P | 90 | S | 45 | S | 45 | S | Week | -26 | P | 100 | S | 50 | S | 50 | S | Week | -23 | P | 90 | S | 45 | S | 45 | S
|  |  | 2025-12-19 |  |  | 2026-01-09 | [8 empty] | 2026-07-24 | [8 empty] | 2026-09-11 | [8 empty] | 2026-10-09 | [8 empty] | 2026-11-20 | [8 empty] | 2026-12-11 | [8 empty] | 2027-01-29 | [8 empty] | 2027-02-19 | [8 empty] | 2027-05-28 | [8 empty] | 2027-06-18 | [8 empty] | 2027-07-09 | [8 empty] | 2027-07-30
| SVER RELEASED PARTS Except for asm's listed below are shipped to CVER timing: Upper Tie Bar Asm FBHP Inner Asm Rocker Inner Asm Plenum Upper Asm Rear W/House Asm Rear End Panel Asm (SUV's Only) |  | WeekM | -107 | M | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 30 | S | 15 | S | 15 | S | Week | -66 | P | 70 | S | 35 | S | 35 | S | Week | -63 | P | 40 | S | 20 | S | 20 | S | Week | -59 | P | 80 | S | 40 | S | 40 | S | Week | -56 | P | 60 | S | 30 | S | 30 | S | Week | -49 | P | 110 | S | 55 | S | 55 | S | Week | -46 | P | 90 | S | 45 | S | 45 | S | Week | -32 | P | 100 | S | 50 | S | 50 | S | Week | -29 | P | 90 | S | 45 | S | 45 | S | Week | -26 | P | 100 | S | 50 | S | 50 | S | Week | -23 | P | 90 | S | 45 | S | 45 | S
|  |  | 2025-12-19 |  |  | 2026-01-09 | [8 empty] | 2026-07-24 | [8 empty] | 2026-10-02 | [8 empty] | 2026-10-23 | [8 empty] | 2026-11-20 | [8 empty] | 2026-12-11 | [8 empty] | 2027-01-29 | [8 empty] | 2027-02-19 | [8 empty] | 2027-05-28 | [8 empty] | 2027-06-18 | [8 empty] | 2027-07-09 | [8 empty] | 2027-07-30
| IVER RELEASED PARTS Except for asm listed below is shipped to CVER timing: Front Impact Beam | * All IVER * (Except Closures) (Except Fenders) (Except Closure OUTERs) | Week | -107 | M | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 30 | S | 15 | S | 15 | S | Week | -63 | P | 70 | S | 35 | S | 35 | S | Week | -60 | P | 40 | S | 20 | S | 20 | S | Week | -59 | P | 80 | S | 40 | S | 40 | S | Week | -56 | P | 60 | S | 30 | S | 30 | S | Week | -49 | P | 110 | S | 55 | S | 55 | S | Week | -46 | P | 90 | S | 45 | S | 45 | S | Week | -32 | P | 100 | S | 50 | S | 50 | S | Week | -29 | P | 90 | S | 45 | S | 45 | S | Week | -26 | P | 100 | S | 50 | S | 50 | S | Week | -23 | P | 90 | S | 45 | S | 45 | S
|  |  | 2025-12-19 |  |  | 2026-01-09 | [8 empty] | 2026-07-24 | [8 empty] | 2026-10-23 | [8 empty] | 2026-11-13 | [8 empty] | 2026-11-20 | [8 empty] | 2026-12-11 | [8 empty] | 2027-01-29 | [8 empty] | 2027-02-19 | [8 empty] | 2027-05-28 | [8 empty] | 2027-06-18 | [8 empty] | 2027-07-09 | [8 empty] | 2027-07-30
|  | * CLOSURES * Doors & Liftgates (NOT Including OUTERs) (NOT Including Fenders) | Week | -107 | M | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 40 | S | 25 | S | 25 | S | Week | -68 | P | 80 | S | 40 | S | 40 | S | Week | -65 | P | 50 | S | 25 | S | 25 | S | Week | -62 | P | 120 | S | 60 | S | 60 | S | Week | -59 | P | 100 | S | 50 | S | 50 | S | Week | -52 | P | 130 | S | 65 | S | 65 | S | Week | -49 | P | 110 | S | 55 | S | 55 | S | Week | -35 | P | 110 | S | 55 | S | 55 | S | Week | -32 | P | 100 | S | 50 | S | 50 | S | Week | -29 | P | 110 | S | 55 | S | 55 | S | Week | -26 | P | 100 | S | 50 | S | 50 | S
|  |  | 2025-12-19 |  |  | 2026-01-09 | [8 empty] | 2026-07-24 | [8 empty] | 2026-09-18 | [8 empty] | 2026-10-09 | [8 empty] | 2026-10-30 | [8 empty] | 2026-11-20 | [8 empty] | 2027-01-08 | [8 empty] | 2027-01-29 | [8 empty] | 2027-05-07 | [8 empty] | 2027-05-28 | [8 empty] | 2027-06-18 | [8 empty] | 2027-07-09
|  | * CLOSURES * (Fenders Only) | N/A |  |  | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 40 | S | 25 | S | 25 | S | N/A | [8 empty] | Week | -58 | P | 50 | S | 25 | S | 25 | S | N/A | [8 empty] | Week | -52 | P | 100 | S | 50 | S | 50 | S | N/A | [8 empty] | Week | -46 | P | 90 | S | 45 | S | 45 | S | N/A | [8 empty] | Week | -29 | P | 90 | S | 45 | S | 45 | S | N/A | [8 empty] | Week | -23 | P | 90 | S | 45 | S | 45 | S
[6 empty] | 2026-01-09 | [8 empty] | 2026-07-24 | [17 empty] | 2026-11-27 | [17 empty] | 2027-01-08 | [17 empty] | 2027-02-19 | [17 empty] | 2027-06-18 | [17 empty] | 2027-07-30
|  | * CLOSURES* (OUTER Panels Only) | N/A |  |  | Week | -104 | P | NA | S | NA | S | NA | S | Week | -76 | P | 50 | S | 30 | S | 30 | S | [9 empty] | Week | -65 | P | 70 | S | 35 | S | 35 | S | [9 empty] | Week | -59 | P | 120 | S | 60 | S | 60 | S | [9 empty] | Week | -49 | P | 130 | S | 65 | S | 65 | S | [9 empty] | Week | -32 | P | 110 | S | 55 | S | 55 | S | [9 empty] | Week | -26 | P | 110 | S | 55 | S | 55 | S
[6 empty] | 2026-01-09 | [8 empty] | 2026-07-24 | [17 empty] | 2026-10-09 | [17 empty] | 2026-11-20 | [17 empty] | 2027-01-29 | [17 empty] | 2027-05-28 | [17 empty] | 2027-07-09
| PTB-C, Tool Try Out, PTB-M |  | Ordered Through PPO System | [29 empty] | N/A
| APPV - Body |  | N/A | [29 empty] | U
| PPV - Body |  | N/A | [29 empty] | U
| MVB NS - Body |  | N/A | [29 empty] | U
| MVB S - Body |  | N/A | [29 empty] | U
| MRD S1.0 |  | N/A | [29 empty] | U
PROGRAM SPECIFIC NOTES:
COMMENTS FOR THE ABOVE TABLE:
Parts delivered to the GM Production Plant/GM facility will be at the contracted production piece price. The supplier is responsible for all shipping costs associated to meet the SOR's MRD dates and quantities at the specified quality level.
+ | Quantity is the same for all body parts ordered through MGO (CVER, SVER, IVER) (Exception is the IVER Closures, quantities are higher)
P | The MRD (Begin) date denotes the start date when the specified total Quantity of parts is required. Additional parts may be requested if part quality improvement is needed. The submission of the specified total Quantity may be all at once at the specified MRD (Begin) date if the part quality is met (per direction of the program Matching Team). Otherwise the submissions will be spread over the specified MRD (Begin) date to the specified MRD (End) Date with part quality improving over subsequent submissions. The exact timing of each submission and the quantity for each submission will be communicated to the supplier (per direction of the Program Matching Team). Note: the MRD (Begin) and part Quantity are program specific and will be managed/determined per direction of the Program Matching Team). Note: the order for the total quantity of a part or assembly number should be placed in the system only once per MRD. If parts are to have multiple deliveries, the quantity and frequency of the deliveries/submissions will be managed through direct communications between the Matching Team and the supplier.
S | Additional pieces and/or rework may be needed if a part quality improvement is required. These additional reworks and/or quantities need to be provided at the supplier's expense.
U | For sheet metal parts supplied by Stamping, the material is already comprehended in the Body Shop Validation Category above. The MRD denotes the required date for Carryover Purchased Part Assembly Plant/New Purchased Part/etc (See the FMA Orders & Tracking Responsibility Table from PI).
M | Mini-Match Review is for critical stampings and assemblies. This will include all 12 Critical Sub Assemblies: Front Rail Asm R/L, Rear Rail Asm R/L, Front W/H Asm R/L, Rear W/H Asm R/L, Upper Tie Bar Asm, SUV D-Pillar Asm R/L, and SUV Rear End Panel as well as others to be specified by the Matching Team. Requirements are listed in GM 10067. Objective is to review parts on checking fixture and in production tools in order to understand issues and drive resolution prior to MRD Matching.
Z | POA = Part Of Assembly: The MRD date when parts are required at a Tier 2 supplier in order to support the "Direct Ship" MRD dates with assemblies. Example #1: A GM Metal Center is a Tier 2 supplier of stamped components to an outside, Tier 1, supplier. Parts from the GM Metal Center, Tier2, are due to the Supplier, Tier 1, on the "POA" date to allow sufficient time for the Tier 1 to build assemblies and deliver to the assembly plant on the "Direct Ship" MRD. Example #2: A GM Metal Center and/or an outside supplier are Tier 2 to a Tier 1, Parma or Flint Metal Center. Parts are due to Parma or Flint Metal Center on the "POA" date to allow sufficient time for the Tier 1, Parma or Flint Metal Center, to build assemblies and deliver to the assembly plant on the "Direct Ship" MRD.
D | Directed Buy Parts require a 10% quantity increase over stated MRD quantity, and are required at the Tier 1 supplier a minimum of 2 (two) weeks prior to the MRD date. Any cost associated with adding more than a 10% quantity are the resposibility of the Tier 1 supplier.
T | Consumption of the MRD metal should be planned as MRD +10 days. There are 10 days allocated to receiving, relocating, and reworking material as necessary.
MINIMUM BIW PART SUBMISSION REQUIREMENTS*
| MRD | Tool Level 9 |  |  |  |  | Quality Level *
| PTB-C, Tool Try out, PTB-M and MRD Matching | Production Intent Tooling - At a minimum: Parts formed, trimmed and pierced off production dies. Assemblies must be off certified GEO tools, Manual Teach robotic welds or production hard guns, Production clamps (May be manually actuated), Production weld and clamping sequence must be followed. Checking fixture should be complete and certified. CMM programs written and complete. Sealer,adhesive and studs may be manually applied with templates. |  |  |  |  | Parts to be reviewed by joint Matching Team and Supplier. Supplier to provide data and action plans to meet MRD Matching requirements.
| MRD APPV | Same as Matching * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  |  | Parts to meet requirements defined in GM10067
| MRD PPV | Same as MRD Matching at a minimum * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MRD NS1.0 | Full Production Tooling- Not necessarily at rate, but fully Automatic and at Homeline location - both for dies and assembly tooling. * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MRD NS2.0 | Full Production Tooling- Not necessarily at rate, but fully Automatic and at Homeline location - both for dies and assembly tooling. * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MVB Saleable | * 100% FULL PPAP Required * (Submit documentation 4 weeks prior to MRD or 2 weeks prior to "PPAP" gate date, whichever comes first) |  |  |  |  | Interim PPAP Salable
* | SUPPLIER REQUIREMETS FOR PART SUBMISSION:
1 | The goal is to build a "Nominal Body" and every part is a "Matching" part
2 | Submit 100% production-tooled parts (no laser trim/cutting, etc.). Any non-production intent processes used to manufacture a submitted part must be communicated & reviewed by the Iterative Matching Team.
3 | Drive part to nominal. If part is not at nominal, communicate where it is off nominal. The supplier must possess knowledge of the quality level of the part, and have data, roadmaps, and process capability studies readily available to determine the quality level of the part and to help resolve build issues.
4 | Provide production parts at the initial submittal date and continue to improve the part (drive part to nominal) to resolve build issues PPAP Status required for Non Saleable and Saleable MRD material prior to shipping. Documentation must be submitted 4 weeks prior to MRD.
5 | Work closely with the Iterative Matching Team led by the VDQM, Vehicle Dimensional Quality Manager to resolve part/build issues
6 | Provide improved parts (when part issues are identified & communicated) in a timely manner, per the Iterative Part Submission process.
7 | Work to the latest part GD&T (datums & tolerances). Parts should be measured using the datum strategy communicated in the GD&T. All critical points are to be driven to nominal.
8 | Work closely with the Matching Team and apply your best efforts to improve part quality and provide a part which will ultimately result in a high quality BIW and a finished vehicle with world-class fit and finish.
9 | Any deviations from the required Tool Level at each MRD must be approved by the Matching Team which includes Supplier Quality, Product Interface, BIW Quality Lead, VDQM, and MP Engineers.
10 | PPAP Status required for Non Saleable and Saleable MRD material prior to shipping. See "MINIMUM BIW PART SUBMISSION REQUIREMENTS*" chart above for specific MRD Documentation submittal requirements.
IN SUMMARY:
a. | Every part is a "Matching" part
b. | The goal of the Iterative Matching process is to build a "Nominal Body"
c. | Your tools have to be done by start of Iterative Matching
d. | Be ready to ship Production-Tooled Parts by start of Iterative Matching
e. | Drive your part (s) and assembly (ies) to nominal
f. | Know your issues with the part (s)
g. | Know the Iterative Matching Team and its Leader
h. | Work with the Team to resolve part/asm build issues
i. | Be there with the Team to resolve part/asm build issues
j. | Be ready to provide data as needed

## T1ULF-2 SWB Cadillac
Appendix E10 Bodyshop Material Requirements
[6 empty] | (2028) T1ULF-2 Cadillac SWB - TIMING MILESTONES SORP (3/6/28) - (Arlington Assembly Plant) | [24 empty] | SORP | [24 empty] | SORP Input: | 2028-03-06
|  |  | Core Panels & Asms | [52 empty] | Do Not DELETE
| T1ULF-2 Cadillac SWB |  | Template Reference: GVDP 5.7 Major Program Framework
[6 empty] | MRD Matching (Arlington) | [9 empty] | MRD APPV (Arlington) | [9 empty] | MRD PPV (Arlington) | [9 empty] | MRD NS1 (Arlingtin) | [9 empty] | MRD NS2 (Arlington)
|  |  | Mini-Match |  |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac
| Program Milestone |  | Review |  |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty
| CVER RELEASED PARTS Including SVER/IVER assemblies listed below: Upper Tie Bar Asm FBHP Inner Asm Rocker Inner Asm Plenum Upper Asm Rear W/House Asm Rear End Panel Asm (SUV's Only) Front Impact Beam |  | Week | -107 | M | Week | -69 | P | 35 | S | Week | -65 | P | 20 | S | Week | -59 | P | 40 | S | Week | -56 | P | 30 | S | Week | -49 | P | 55 | S | Week | -46 | P | 45 | S | Week | -32 | P | 50 | S | Week | -29 | P | 45 | S | Week | -26 | P | 50 | S | Week | -23 | P | 45 | S
|  |  | 2026-02-13 |  |  | 2026-11-06 |  |  |  |  | 2026-12-04 |  |  |  |  | 2027-01-15 |  |  |  |  | 2027-02-05 |  |  |  |  | 2027-03-26 |  |  |  |  | 2027-04-16 |  |  |  |  | 2027-07-23 |  |  |  |  | 2027-08-13 |  |  |  |  | 2027-09-03 |  |  |  |  | 2027-09-24
| SVER RELEASED PARTS Except for asm's listed below are shipped to CVER timing: Upper Tie Bar Asm FBHP Inner Asm Rocker Inner Asm Plenum Upper Asm Rear W/House Asm Rear End Panel Asm (SUV's Only) |  | WeekM | -107 | M | Week | -66 | P | 35 | S | Week | -63 | P | 20 | S | Week | -59 | P | 40 | S | Week | -56 | P | 30 | S | Week | -49 | P | 55 | S | Week | -46 | P | 45 | S | Week | -32 | P | 50 | S | Week | -29 | P | 45 | S | Week | -26 | P | 50 | S | Week | -23 | P | 45 | S
|  |  | 2026-02-13 |  |  | 2026-11-27 |  |  |  |  | 2026-12-18 |  |  |  |  | 2027-01-15 |  |  |  |  | 2027-02-05 |  |  |  |  | 2027-03-26 |  |  |  |  | 2027-04-16 |  |  |  |  | 2027-07-23 |  |  |  |  | 2027-08-13 |  |  |  |  | 2027-09-03 |  |  |  |  | 2027-09-24
| IVER RELEASED PARTS Except for asm listed below is shipped to CVER timing: Front Impact Beam | * All IVER * (Except Closures) (Except Fenders) (Except Closure OUTERs) | Week | -107 | M | Week | -63 | P | 35 | S | Week | -60 | P | 20 | S | Week | -59 | P | 40 | S | Week | -56 | P | 30 | S | Week | -49 | P | 55 | S | Week | -46 | P | 45 | S | Week | -32 | P | 50 | S | Week | -29 | P | 45 | S | Week | -26 | P | 50 | S | Week | -23 | P | 45 | S
|  |  | 2026-02-13 |  |  | 2026-12-18 |  |  |  |  | 2027-01-08 |  |  |  |  | 2027-01-15 |  |  |  |  | 2027-02-05 |  |  |  |  | 2027-03-26 |  |  |  |  | 2027-04-16 |  |  |  |  | 2027-07-23 |  |  |  |  | 2027-08-13 |  |  |  |  | 2027-09-03 |  |  |  |  | 2027-09-24
|  | * CLOSURES * Doors & Liftgates (NOT Including OUTERs) (NOT Including Fenders) | Week | -107 | M | Week | -68 | P | 40 | S | Week | -65 | P | 25 | S | Week | -62 | P | 60 | S | Week | -59 | P | 50 | S | Week | -52 | P | 65 | S | Week | -49 | P | 55 | S | Week | -35 | P | 55 | S | Week | -32 | P | 50 | S | Week | -29 | P | 55 | S | Week | -26 | P | 50 | S
|  |  | 2026-02-13 |  |  | 2026-11-13 |  |  |  |  | 2026-12-04 |  |  |  |  | 2026-12-25 |  |  |  |  | 2027-01-15 |  |  |  |  | 2027-03-05 |  |  |  |  | 2027-03-26 |  |  |  |  | 2027-07-02 |  |  |  |  | 2027-07-23 |  |  |  |  | 2027-08-13 |  |  |  |  | 2027-09-03
|  | * CLOSURES * (Fenders Only) | N/A |  |  | N/A |  |  |  |  | Week | -58 | P | 25 | S | N/A |  |  |  |  | Week | -52 | P | 50 | S | N/A |  |  |  |  | Week | -46 | P | 45 | S | N/A |  |  |  |  | Week | -29 | P | 45 | S | N/A |  |  |  |  | Week | -23 | P | 45 | S
[11 empty] | 2027-01-22 | [9 empty] | 2027-03-05 | [9 empty] | 2027-04-16 | [9 empty] | 2027-08-13 | [9 empty] | 2027-09-24
|  | * CLOSURES* (OUTER Panels Only) | N/A | [7 empty] | Week | -65 | P | 35 | S | [5 empty] | Week | -59 | P | 60 | S | [5 empty] | Week | -49 | P | 65 | S | [5 empty] | Week | -32 | P | 55 | S | [5 empty] | Week | -26 | P | 55 | S
[11 empty] | 2026-12-04 | [9 empty] | 2027-01-15 | [9 empty] | 2027-03-26 | [9 empty] | 2027-07-23 | [9 empty] | 2027-09-03
| PTB-C, Tool Try Out, PTB-M |  | Ordered Through PPO System | [7 empty] | N/A
| APPV - Body |  | N/A | [7 empty] | U
| PPV - Body |  | N/A | [7 empty] | U
| MVB NS - Body |  | N/A | [7 empty] | U
| MVB S - Body |  | N/A | [7 empty] | U
| MRD S1.0 |  | N/A | [7 empty] | U
PROGRAM SPECIFIC NOTES:
COMMENTS FOR THE ABOVE TABLE:
Parts delivered to the GM Production Plant/GM facility will be at the contracted production piece price. The supplier is responsible for all shipping costs associated to meet the SOR's MRD dates and quantities at the specified quality level.
+ | Quantity is the same for all body parts ordered through MGO (CVER, SVER, IVER) (Exception is the IVER Closures, quantities are higher)
P | The MRD (Begin) date denotes the start date when the specified total Quantity of parts is required. Additional parts may be requested if part quality improvement is needed. The submission of the specified total Quantity may be all at once at the specified MRD (Begin) date if the part quality is met (per direction of the program Matching Team). Otherwise the submissions will be spread over the specified MRD (Begin) date to the specified MRD (End) Date with part quality improving over subsequent submissions. The exact timing of each submission and the quantity for each submission will be communicated to the supplier (per direction of the Program Matching Team). Note: the MRD (Begin) and part Quantity are program specific and will be managed/determined per direction of the Program Matching Team). Note: the order for the total quantity of a part or assembly number should be placed in the system only once per MRD. If parts are to have multiple deliveries, the quantity and frequency of the deliveries/submissions will be managed through direct communications between the Matching Team and the supplier.
S | Additional pieces and/or rework may be needed if a part quality improvement is required. These additional reworks and/or quantities need to be provided at the supplier's expense.
U | For sheet metal parts supplied by Stamping, the material is already comprehended in the Body Shop Validation Category above. The MRD denotes the required date for Carryover Purchased Part Assembly Plant/New Purchased Part/etc (See the FMA Orders & Tracking Responsibility Table from PI).
M | Mini-Match Review is for critical stampings and assemblies. This will include all 12 Critical Sub Assemblies: Front Rail Asm R/L, Rear Rail Asm R/L, Front W/H Asm R/L, Rear W/H Asm R/L, Upper Tie Bar Asm, SUV D-Pillar Asm R/L, and SUV Rear End Panel as well as others to be specified by the Matching Team. Requirements are listed in GM 10067. Objective is to review parts on checking fixture and in production tools in order to understand issues and drive resolution prior to MRD Matching.
Z | POA = Part Of Assembly: The MRD date when parts are required at a Tier 2 supplier in order to support the "Direct Ship" MRD dates with assemblies. Example #1: A GM Metal Center is a Tier 2 supplier of stamped components to an outside, Tier 1, supplier. Parts from the GM Metal Center, Tier2, are due to the Supplier, Tier 1, on the "POA" date to allow sufficient time for the Tier 1 to build assemblies and deliver to the assembly plant on the "Direct Ship" MRD. Example #2: A GM Metal Center and/or an outside supplier are Tier 2 to a Tier 1, Parma or Flint Metal Center. Parts are due to Parma or Flint Metal Center on the "POA" date to allow sufficient time for the Tier 1, Parma or Flint Metal Center, to build assemblies and deliver to the assembly plant on the "Direct Ship" MRD.
D | Directed Buy Parts require a 10% quantity increase over stated MRD quantity, and are required at the Tier 1 supplier a minimum of 2 (two) weeks prior to the MRD date. Any cost associated with adding more than a 10% quantity are the resposibility of the Tier 1 supplier.
T | Consumption of the MRD metal should be planned as MRD +10 days. There are 10 days allocated to receiving, relocating, and reworking material as necessary.
MINIMUM BIW PART SUBMISSION REQUIREMENTS*
| MRD | Tool Level 9
| PTB-C, Tool Try out, PTB-M and MRD Matching | Production Intent Tooling - At a minimum: Parts formed, trimmed and pierced off production dies. Assemblies must be off certified GEO tools, Manual Teach robotic welds or production hard guns, Production clamps (May be manually actuated), Production weld and clamping sequence must be followed. Checking fixture should be complete and certified. CMM programs written and complete. Sealer,adhesive and studs may be manually applied with templates. |  |  |  | Parts to be reviewed by joint Matching Team and Supplier. Supplier to provide data and action plans to meet MRD Matching requirements.
| MRD APPV | Same as Matching * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  | Parts to meet requirements defined in GM10067
| MRD PPV | Same as MRD Matching at a minimum * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MRD NS1.0 | Full Production Tooling- Not necessarily at rate, but fully Automatic and at Homeline location - both for dies and assembly tooling. * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MRD NS2.0 | Full Production Tooling- Not necessarily at rate, but fully Automatic and at Homeline location - both for dies and assembly tooling. * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MVB Saleable | * 100% FULL PPAP Required * (Submit documentation 4 weeks prior to MRD or 2 weeks prior to "PPAP" gate date, whichever comes first) |  |  |  | Interim PPAP Salable
* | SUPPLIER REQUIREMETS FOR PART SUBMISSION:
1 | The goal is to build a "Nominal Body" and every part is a "Matching" part
2 | Submit 100% production-tooled parts (no laser trim/cutting, etc.). Any non-production intent processes used to manufacture a submitted part must be communicated & reviewed by the Iterative Matching Team.
3 | Drive part to nominal. If part is not at nominal, communicate where it is off nominal. The supplier must possess knowledge of the quality level of the part, and have data, roadmaps, and process capability studies readily available to determine the quality level of the part and to help resolve build issues.
4 | Provide production parts at the initial submittal date and continue to improve the part (drive part to nominal) to resolve build issues PPAP Status required for Non Saleable and Saleable MRD material prior to shipping. Documentation must be submitted 4 weeks prior to MRD.
5 | Work closely with the Iterative Matching Team led by the VDQM, Vehicle Dimensional Quality Manager to resolve part/build issues
6 | Provide improved parts (when part issues are identified & communicated) in a timely manner, per the Iterative Part Submission process.
7 | Work to the latest part GD&T (datums & tolerances). Parts should be measured using the datum strategy communicated in the GD&T. All critical points are to be driven to nominal.
8 | Work closely with the Matching Team and apply your best efforts to improve part quality and provide a part which will ultimately result in a high quality BIW and a finished vehicle with world-class fit and finish.
9 | Any deviations from the required Tool Level at each MRD must be approved by the Matching Team which includes Supplier Quality, Product Interface, BIW Quality Lead, VDQM, and MP Engineers.
10 | PPAP Status required for Non Saleable and Saleable MRD material prior to shipping. See "MINIMUM BIW PART SUBMISSION REQUIREMENTS*" chart above for specific MRD Documentation submittal requirements.
IN SUMMARY:
a. | Every part is a "Matching" part
b. | The goal of the Iterative Matching process is to build a "Nominal Body"
c. | Your tools have to be done by start of Iterative Matching
d. | Be ready to ship Production-Tooled Parts by start of Iterative Matching
e. | Drive your part (s) and assembly (ies) to nominal
f. | Know your issues with the part (s)
g. | Know the Iterative Matching Team and its Leader
h. | Work with the Team to resolve part/asm build issues
i. | Be there with the Team to resolve part/asm build issues
j. | Be ready to provide data as needed

## T1YLF-2 LWB Cadillac
Appendix E10 Bodyshop Material Requirements
[6 empty] | (2028) T1YLF-2 Cadillac LWB - TIMING MILESTONES SORP (3/6/28) - (Arlington Assembly Plant) | [24 empty] | SORP | [24 empty] | SORP Input: | 2028-03-06
|  |  | Core Panels & Asms | [52 empty] | Do Not DELETE
| T1YLF-2 Cadillac LWB |  | Template Reference: GVDP 5.7 Major Program Framework
[6 empty] | MRD Matching (Arlington) | [9 empty] | MRD APPV (Arlington) | [9 empty] | MRD PPV (Arlington) | [9 empty] | MRD NS1 (Arlingtin) | [9 empty] | MRD NS2 (Arlington)
|  |  | Mini-Match |  |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac |  | POA Z T |  |  | Cadillac |  | Direct Ship T |  |  | Cadillac
| Program Milestone |  | Review |  |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty |  | (Begin)P |  |  | Qty
| CVER RELEASED PARTS Including SVER/IVER assemblies listed below: Upper Tie Bar Asm FBHP Inner Asm Rocker Inner Asm Plenum Upper Asm Rear W/House Asm Rear End Panel Asm (SUV's Only) Front Impact Beam |  | Week | -107 | M | Week | -69 | P | 35 | S | Week | -65 | P | 20 | S | Week | -59 | P | 40 | S | Week | -56 | P | 30 | S | Week | -49 | P | 55 | S | Week | -46 | P | 45 | S | Week | -32 | P | 50 | S | Week | -29 | P | 45 | S | Week | -26 | P | 50 | S | Week | -23 | P | 45 | S
|  |  | 2026-02-13 |  |  | 2026-11-06 |  |  |  |  | 2026-12-04 |  |  |  |  | 2027-01-15 |  |  |  |  | 2027-02-05 |  |  |  |  | 2027-03-26 |  |  |  |  | 2027-04-16 |  |  |  |  | 2027-07-23 |  |  |  |  | 2027-08-13 |  |  |  |  | 2027-09-03 |  |  |  |  | 2027-09-24
| SVER RELEASED PARTS Except for asm's listed below are shipped to CVER timing: Upper Tie Bar Asm FBHP Inner Asm Rocker Inner Asm Plenum Upper Asm Rear W/House Asm Rear End Panel Asm (SUV's Only) |  | WeekM | -107 | M | Week | -66 | P | 35 | S | Week | -63 | P | 20 | S | Week | -59 | P | 40 | S | Week | -56 | P | 30 | S | Week | -49 | P | 55 | S | Week | -46 | P | 45 | S | Week | -32 | P | 50 | S | Week | -29 | P | 45 | S | Week | -26 | P | 50 | S | Week | -23 | P | 45 | S
|  |  | 2026-02-13 |  |  | 2026-11-27 |  |  |  |  | 2026-12-18 |  |  |  |  | 2027-01-15 |  |  |  |  | 2027-02-05 |  |  |  |  | 2027-03-26 |  |  |  |  | 2027-04-16 |  |  |  |  | 2027-07-23 |  |  |  |  | 2027-08-13 |  |  |  |  | 2027-09-03 |  |  |  |  | 2027-09-24
| IVER RELEASED PARTS Except for asm listed below is shipped to CVER timing: Front Impact Beam | * All IVER * (Except Closures) (Except Fenders) (Except Closure OUTERs) | Week | -107 | M | Week | -63 | P | 35 | S | Week | -60 | P | 20 | S | Week | -59 | P | 40 | S | Week | -56 | P | 30 | S | Week | -49 | P | 55 | S | Week | -46 | P | 45 | S | Week | -32 | P | 50 | S | Week | -29 | P | 45 | S | Week | -26 | P | 50 | S | Week | -23 | P | 45 | S
|  |  | 2026-02-13 |  |  | 2026-12-18 |  |  |  |  | 2027-01-08 |  |  |  |  | 2027-01-15 |  |  |  |  | 2027-02-05 |  |  |  |  | 2027-03-26 |  |  |  |  | 2027-04-16 |  |  |  |  | 2027-07-23 |  |  |  |  | 2027-08-13 |  |  |  |  | 2027-09-03 |  |  |  |  | 2027-09-24
|  | * CLOSURES * Doors & Liftgates (NOT Including OUTERs) (NOT Including Fenders) | Week | -107 | M | Week | -68 | P | 40 | S | Week | -65 | P | 25 | S | Week | -62 | P | 60 | S | Week | -59 | P | 50 | S | Week | -52 | P | 65 | S | Week | -49 | P | 55 | S | Week | -35 | P | 55 | S | Week | -32 | P | 50 | S | Week | -29 | P | 55 | S | Week | -26 | P | 50 | S
|  |  | 2026-02-13 |  |  | 2026-11-13 |  |  |  |  | 2026-12-04 |  |  |  |  | 2026-12-25 |  |  |  |  | 2027-01-15 |  |  |  |  | 2027-03-05 |  |  |  |  | 2027-03-26 |  |  |  |  | 2027-07-02 |  |  |  |  | 2027-07-23 |  |  |  |  | 2027-08-13 |  |  |  |  | 2027-09-03
|  | * CLOSURES * (Fenders Only) | N/A |  |  | N/A |  |  |  |  | Week | -58 | P | 25 | S | N/A |  |  |  |  | Week | -52 | P | 50 | S | N/A |  |  |  |  | Week | -46 | P | 45 | S | N/A |  |  |  |  | Week | -29 | P | 45 | S | N/A |  |  |  |  | Week | -23 | P | 45 | S
[11 empty] | 2027-01-22 | [9 empty] | 2027-03-05 | [9 empty] | 2027-04-16 | [9 empty] | 2027-08-13 | [9 empty] | 2027-09-24
|  | * CLOSURES* (OUTER Panels Only) | N/A | [7 empty] | Week | -65 | P | 35 | S | [5 empty] | Week | -59 | P | 60 | S | [5 empty] | Week | -49 | P | 65 | S | [5 empty] | Week | -32 | P | 55 | S | [5 empty] | Week | -26 | P | 55 | S
[11 empty] | 2026-12-04 | [9 empty] | 2027-01-15 | [9 empty] | 2027-03-26 | [9 empty] | 2027-07-23 | [9 empty] | 2027-09-03
| PTB-C, Tool Try Out, PTB-M |  | Ordered Through PPO System | [7 empty] | N/A
| APPV - Body |  | N/A | [7 empty] | U
| PPV - Body |  | N/A | [7 empty] | U
| MVB NS - Body |  | N/A | [7 empty] | U
| MVB S - Body |  | N/A | [7 empty] | U
| MRD S1.0 |  | N/A | [7 empty] | U
PROGRAM SPECIFIC NOTES:
COMMENTS FOR THE ABOVE TABLE:
Parts delivered to the GM Production Plant/GM facility will be at the contracted production piece price. The supplier is responsible for all shipping costs associated to meet the SOR's MRD dates and quantities at the specified quality level.
+ | Quantity is the same for all body parts ordered through MGO (CVER, SVER, IVER) (Exception is the IVER Closures, quantities are higher)
P | The MRD (Begin) date denotes the start date when the specified total Quantity of parts is required. Additional parts may be requested if part quality improvement is needed. The submission of the specified total Quantity may be all at once at the specified MRD (Begin) date if the part quality is met (per direction of the program Matching Team). Otherwise the submissions will be spread over the specified MRD (Begin) date to the specified MRD (End) Date with part quality improving over subsequent submissions. The exact timing of each submission and the quantity for each submission will be communicated to the supplier (per direction of the Program Matching Team). Note: the MRD (Begin) and part Quantity are program specific and will be managed/determined per direction of the Program Matching Team). Note: the order for the total quantity of a part or assembly number should be placed in the system only once per MRD. If parts are to have multiple deliveries, the quantity and frequency of the deliveries/submissions will be managed through direct communications between the Matching Team and the supplier.
S | Additional pieces and/or rework may be needed if a part quality improvement is required. These additional reworks and/or quantities need to be provided at the supplier's expense.
U | For sheet metal parts supplied by Stamping, the material is already comprehended in the Body Shop Validation Category above. The MRD denotes the required date for Carryover Purchased Part Assembly Plant/New Purchased Part/etc (See the FMA Orders & Tracking Responsibility Table from PI).
M | Mini-Match Review is for critical stampings and assemblies. This will include all 12 Critical Sub Assemblies: Front Rail Asm R/L, Rear Rail Asm R/L, Front W/H Asm R/L, Rear W/H Asm R/L, Upper Tie Bar Asm, SUV D-Pillar Asm R/L, and SUV Rear End Panel as well as others to be specified by the Matching Team. Requirements are listed in GM 10067. Objective is to review parts on checking fixture and in production tools in order to understand issues and drive resolution prior to MRD Matching.
Z | POA = Part Of Assembly: The MRD date when parts are required at a Tier 2 supplier in order to support the "Direct Ship" MRD dates with assemblies. Example #1: A GM Metal Center is a Tier 2 supplier of stamped components to an outside, Tier 1, supplier. Parts from the GM Metal Center, Tier2, are due to the Supplier, Tier 1, on the "POA" date to allow sufficient time for the Tier 1 to build assemblies and deliver to the assembly plant on the "Direct Ship" MRD. Example #2: A GM Metal Center and/or an outside supplier are Tier 2 to a Tier 1, Parma or Flint Metal Center. Parts are due to Parma or Flint Metal Center on the "POA" date to allow sufficient time for the Tier 1, Parma or Flint Metal Center, to build assemblies and deliver to the assembly plant on the "Direct Ship" MRD.
D | Directed Buy Parts require a 10% quantity increase over stated MRD quantity, and are required at the Tier 1 supplier a minimum of 2 (two) weeks prior to the MRD date. Any cost associated with adding more than a 10% quantity are the resposibility of the Tier 1 supplier.
T | Consumption of the MRD metal should be planned as MRD +10 days. There are 10 days allocated to receiving, relocating, and reworking material as necessary.
MINIMUM BIW PART SUBMISSION REQUIREMENTS*
| MRD | Tool Level 9
| PTB-C, Tool Try out, PTB-M and MRD Matching | Production Intent Tooling - At a minimum: Parts formed, trimmed and pierced off production dies. Assemblies must be off certified GEO tools, Manual Teach robotic welds or production hard guns, Production clamps (May be manually actuated), Production weld and clamping sequence must be followed. Checking fixture should be complete and certified. CMM programs written and complete. Sealer,adhesive and studs may be manually applied with templates. |  |  |  | Parts to be reviewed by joint Matching Team and Supplier. Supplier to provide data and action plans to meet MRD Matching requirements.
| MRD APPV | Same as Matching * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  | Parts to meet requirements defined in GM10067
| MRD PPV | Same as MRD Matching at a minimum * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MRD NS1.0 | Full Production Tooling- Not necessarily at rate, but fully Automatic and at Homeline location - both for dies and assembly tooling. * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MRD NS2.0 | Full Production Tooling- Not necessarily at rate, but fully Automatic and at Homeline location - both for dies and assembly tooling. * PPAP Requirement of NonSaleable Status * (Submit documentation 2 weeks prior to "PPAP NS BIW" gate date) |  |  |  | Quality Parts With Specified Matching Improvements; meet GM10067 requirements
| MVB Saleable | * 100% FULL PPAP Required * (Submit documentation 4 weeks prior to MRD or 2 weeks prior to "PPAP" gate date, whichever comes first) |  |  |  | Interim PPAP Salable
* | SUPPLIER REQUIREMETS FOR PART SUBMISSION:
1 | The goal is to build a "Nominal Body" and every part is a "Matching" part
2 | Submit 100% production-tooled parts (no laser trim/cutting, etc.). Any non-production intent processes used to manufacture a submitted part must be communicated & reviewed by the Iterative Matching Team.
3 | Drive part to nominal. If part is not at nominal, communicate where it is off nominal. The supplier must possess knowledge of the quality level of the part, and have data, roadmaps, and process capability studies readily available to determine the quality level of the part and to help resolve build issues.
4 | Provide production parts at the initial submittal date and continue to improve the part (drive part to nominal) to resolve build issues PPAP Status required for Non Saleable and Saleable MRD material prior to shipping. Documentation must be submitted 4 weeks prior to MRD.
5 | Work closely with the Iterative Matching Team led by the VDQM, Vehicle Dimensional Quality Manager to resolve part/build issues
6 | Provide improved parts (when part issues are identified & communicated) in a timely manner, per the Iterative Part Submission process.
7 | Work to the latest part GD&T (datums & tolerances). Parts should be measured using the datum strategy communicated in the GD&T. All critical points are to be driven to nominal.
8 | Work closely with the Matching Team and apply your best efforts to improve part quality and provide a part which will ultimately result in a high quality BIW and a finished vehicle with world-class fit and finish.
9 | Any deviations from the required Tool Level at each MRD must be approved by the Matching Team which includes Supplier Quality, Product Interface, BIW Quality Lead, VDQM, and MP Engineers.
10 | PPAP Status required for Non Saleable and Saleable MRD material prior to shipping. See "MINIMUM BIW PART SUBMISSION REQUIREMENTS*" chart above for specific MRD Documentation submittal requirements.
IN SUMMARY:
a. | Every part is a "Matching" part
b. | The goal of the Iterative Matching process is to build a "Nominal Body"
c. | Your tools have to be done by start of Iterative Matching
d. | Be ready to ship Production-Tooled Parts by start of Iterative Matching
e. | Drive your part (s) and assembly (ies) to nominal
f. | Know your issues with the part (s)
g. | Know the Iterative Matching Team and its Leader
h. | Work with the Team to resolve part/asm build issues
i. | Be there with the Team to resolve part/asm build issues
j. | Be ready to provide data as needed

## Revisions
Release and Revisions to APPENDIX E10
ID | Revision Date | Revision Description (must include section, test, etc., changed) | Approving Organization | Author
| 2015-11-02 | Initial Release | BIW Manufacturing - PI | Carl Herter
| 2015-11-13 | CG number added | BIW Manufacturing - PI | B Miller
| 2016-05-02 | DIW Parts Only revised to Front / Rear / Side Closures. Title, timing and weeks revised from GVDP 5.2 to GVDP 5.3 Major Program Timing and MRD quantities revised to updated MRD Chart. | BIW Manufacturing - PI | B Miller
| 2018-10-03 | Template updated to reflect GVDP 5.4 changes to the Tombstone Chart dated 26-Jul-18. | BIW Manufacturing - PI | Robert Richter
| 2019-02-21 | Added "Revision" tab to the document for change tracking | BIW Manufacturing - PI | Robert Richter
| 2019-02-21 | Added "Tombstone Chart" tab to the document as requested by E10 Peer Group review, 2/19/19 | BIW Manufacturing - PI | Robert Richter
| 2019-02-22 | Added "Program Specific Notes" section as requested by E10 Peer Group review, 2/19/19 | BIW Manufacturing - PI | Robert Richter
| 2019-02-25 | Added POA "Date" and "Qty" columns to the chart as requested by E10 Peer Group review, 2/19/19. | BIW Manufacturing - PI | Robert Richter
| 2019-02-26 | Added Multi Program version of the template as requested be E10 Peer Group review, 2/19/19. | BIW Manufacturing - PI | Robert Richter
| 2019-02-28 | Added "Notes" to "Tombstone" tab and included location in ME Body website Forms library for the location of the latest chart. | BIW Manufacturing - PI | Robert Richter
| 2019-03-06 | Added "Z" suffix to the "POA" nomenclature and provided the appropriate LEGEND for "Z". | BIW Manufacturing - PI | Robert Richter
| 2019-04-16 | Added row to IVER to cover Closure "OUTER" panel specific requirements | BIW Manufacturing - PI | Robert Richter
| 2019-04-25 | Added row to IVER to cover Closure "Fender" specific requirements | BIW Manufacturing - PI | Robert Richter
| 2019-04-25 | Loaded updated "Tombstone" chart that includes POA note for "Closure" specific parts. | BIW Manufacturing - PI | Robert Richter
| 2019-05-15 | Revised Fender MRD requirements for PPV and MVBNS to reflect Direct Ship weeks. Fenders have split requirement dates. Matching and APPV are early and then PPV and MVBNS follow Direct Ship Dates and Qtys. | BIW Manufacturing - PI | Robert Richter
| 2019-05-20 | Added latest MRD Template to reflect GVDP 5.5. NO changes to our ME Body Requirements due to GVDP 5.5. | BIW Manufacturing - PI | Robert Richter
| 2019-06-11 | Error Identified on the "E10 Template Multiple" form. The MVBNS "Outer" panel quantity was identified as "60" and should read "55". Template corrected. | BIW Manufacturing - PI | Robert Richter
| 2021-09-14 | Added Rear W/House to CVER MRD requirement for clarity. RR W/House is a SVER released part but required for CVER MRD. | BIW Manufacturing - PI | Robert Richter
| 2021-11-03 | Added PPAP documentation notes in the "MINIMUM BIW PART SUBMISSION REQUIREMENTS*" Chart under NS1.0, NS2.0, & MVB Saleable. "(Submit documentation 2 weeks prior to MRD)" Requested by Gjovan Gojcaj, Sangeeta LaForges, Dave Galloway, Shalesh Patel. | BIW Manufacturing - PI | Robert Richter
| 2021-11-03 | Addd "Rework" to note "S" in the "Comment" section | BIW Manufacturing - PI | Robert Richter
| 2021-11-03 | Added note "D" in the "Comments" section | BIW Manufacturing - PI | Robert Richter
| 2021-11-03 | Added requirement "10" in the "SUPPLIER REQUIREMETS FOR PART SUBMISSION:" section | BIW Manufacturing - PI | Robert Richter
| 2022-01-10 | Added PPAP submit timing requirements in "MINIMUM BIW PART SUBMISSION REQUIREMENTS" chart for MRD APPV and beyond. | BIW Manufacturing - PI | Robert Richter
| 2022-01-10 | revised requirement "10" in the "SUPPLIER REQUIREMETS FOR PART SUBMISSION:" section. Second sentence revised to reference chart for submittal requirements. | BIW Manufacturing - PI | Robert Richter
| 2022-01-17 | Per discussion with Terry Barber, the Mini Match date has been changed from "Direct ship" -3 weeks to "Direct Ship" -4 weeks. | BIW Manufacturing - PI | Robert Richter
| 2022-01-17 | Updated Tombstone Chart to reflect "Mini Match" dates at "DS" -4 weeks | BIW Manufacturing - PI | Robert Richter
| 2022-03-10 | Corrected Note #4 to read "Documentation must be submitted 4 weeks prior to MRD". Prior note read 2 weeks. | BIW Manufacturing - PI | Robert Richter
| 2022-08-17 | Updated charts to reflect GVDP5.7. GVDP5.7 Changes did not impact our MRD's, so this is only a nomenclature update. | BIW Manufacturing - PI | Robert Richter
| 2023-02-15 | Added note "T" to comments section to clarify and replicate the long standing note on the "Tombstone" chart that specifies material is not to be planned for consumption until MRD +10 days. | BIW Manufacturing - PI | Robert Richter
| 2023-02-20 | Added Rear End Panel Asm, SVER part, to the CVER list of parts required for Matching. (Applies to SUV's only! Cars remain as Inner Framing/Framing 1) | BIW Manufacturing - PI | Robert Richter
| 2024-07-23 | Original Release for T1-2 SUV Program | BIW Manufacturing - PI | Jason Schmidt