## Supplier Info
Supplier Name and Address
Supplier Address
(Supplier Duns Number(s): XXXX )
Position | Name | % Allocation to Program | Cell Phone Number | Email Address
Program Manager
Account Manager
General Manager
AGM (Finance)
AGM (Production)
Plant Manager
Quality Manager
APQP Engineer
Quality Engineer
Engineering Manager
Die Engineer
Assembly Engineer

## MASTER Sheet
Vehicle Program |  |  |  |  | Template Revised on: June 19th, 2023 | [7 empty] | MATERIAL | [7 empty] | DIE INFORMATION / TIMING | [28 empty] | ASSEMBLY CELL INFORMATION / TIMING | [18 empty] | PART PEDIGREE FORCAST / PAST SCORES
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | TKVxxx | DXX22000 | [17 empty] | PLAN | ACTUAL | PLAN | ACTUAL | % | PLAN | ACTUAL | PLAN | ACTUAL | Previous % | Current % | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL |  |  |  | PLAN | ACTUAL | % | PLAN | ACTUAL | PLAN | ACTUAL | % | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | Mini-Match |  | MRD Matching |  | MRD APPV |  | MRD PPV |  | MRD NS1 |  | MRD NS2
CVER / SVER / IVER/GA | Mini Match Req'd | Data Review Reqd | GDIS Required | Surface Review Required | DES File Recieved | Critical Stamping | Part Number | Part Description | PART PICTURE FREEZE PANES CELL BELOW RIGHT SIDE | Right Hand (RH), Left Hand (LH), Cross Car (CC) | Supplier Location DUNS # | Product Design Engineer (DRE) | Material Specification | Material Thickness (mm) | Release Level at TKO (Tooling Kick Off) | Coil Width (mm) | Pitch (mm) | Coil Width Availability CONFIRMED (date) | Material On Contract (date) | Tooling Purchase Order (TPO) (Date) | Stamping Plant (name) | Stamping Plant (location) | Die Tooling Source (name) | Die Tooling Build Source (location) | Mfg. Process (Transfer, Prog, Tandem, Rollform, Casting, Extrusion) | # of Mfg Operations/ Stations | Formability/ Layout Review w/GM (date) |  | Die Design Start (date) |  | Die Design % Complete (0-25-50-75-100%) | Die Design Review w/GM (date) |  | Die Constr. Start (date) |  | Die Constr. % Complete (see TASKS tab) |  | Die Constr. Complete First Part to Gauge (FPG) (date) (Die @ 65%) |  | Die Tryout Quality Loop 1 (completed date) (Die @ 70%) |  | Die Tryout Quality Loop 2 (completed date) (Die @ 75%) |  | Die Ship Out (date) (Die @ 90%) |  | Die Arrived Homeline (date) (Die @ 95%) |  | Die Homeline Tryout Complete (date) (Die @ 100%) |  | Asm Cell Source (name) | Asm Cell Build Source (location) | Tooling Kick Off (TKO) (date) | Asm Supplier on Contract (date) |  | Asm Cell Design % Complete (0-25-50-75-100%) | Asm Cell Design Review w/GM (date) |  | Asm Cell Construction Start (date) |  | Asm Cell % Complete (0-25-50-75-100%) | Asm Cell Construction Review (date) |  | Asm Cell Complete (date) |  | Asm Cell Ship Out to Homeline (date) |  | Asm Cell Arrived Homeline Power-On (date) |  | MINI-MATCH PAST Score | Part Pedigree LVT , PT | Matching 1 Part Score (MRD0) | Part Pedigree LVT , PT | APPV PAST Score | Part Pedigree LVT , PT | PPV PAST Score (MRD1) | Part Pedigree LVT , PT | NS1 PAST Score (MRD2) | Part Pedigree LVT , PT | NS2 PAST Score (MRD3) | Part Pedigree LVT , PT | Comments
Note on B3: Critical Assy requires Mini Match Event DES file to be provided Asm weld cell review w/GM required.
Note on C3: No Mini Match required. Data review with GM req'd prior to shipping.
Note on G3: Critical stampings must pass supplier formabiltiy. Die review w/GM req'd.
Note on H3: Track all part numbers. Current number shipping in black bold. If part number changes for next MRD, highlight that in red bold.
Note on I3: Use correct part name as these do not change through life of program
Note on L3: Author: DUNS name Location
Note on T3: Internal date when material is bought for die tryout
Note on AW3: All tooling to be homeline in time to run MRD2 parts
Note on BE3: To be completed when designs are 80% complete.
Note on BL3: Make sure you and the supplier agree on what "complete" means
Note on BP3: All tooling to be homeline in order to run MRD2 parts
Note on BR3: CVER target six weeks before MRD0. SVER and IVER target 3 weeks before MRD0
Note on BS3: LVT = Low Volume Tooling PT = Production Tooling
Note on BU3: LVT = Low Volume Tooling PT = Production Tooling
Note on BW3: LVT = Low Volume Tooling PT = Production Tooling
Note on BY3: LVT = Low Volume Tooling PT = Production Tooling
Note on CA3: LVT = Low Volume Tooling PT = Production Tooling
Note on CC3: LVT = Low Volume Tooling PT = Production Tooling

## TASKS-Die %'s
# | Tasks / Cast Die | % | # | Tasks / Steel Progressive Die | %
1 | Process Completed / Simulation | 5 | 1 | Strip Layout / Simulation | 5
2 | Die Design at 70% | 10 | 2 | Die Design at 70% | 10
3 | Patterns Complete | 15 | 3 | Surfacing & CNC Programing | 15
4 | Patterns at Foundry | 20 | 4 | Majority of Material Received | 20
5 | Castings Poured | 25 | 5 | 2D Machining Completed | 25
6 | Majority of Material Ordered | 30 | 6 | 3D Machining Completed | 30
7 | Castings/Majority Material Received | 35 | 7 | Heat Treat Completed | 35
8 | 2D Machining Completed | 40 | 8 | Assembly # 1 Completed | 40
9 | Assembly # 1 Completed | 45 | 9 | Initial Tryout & Trim Development (tryout mat'l / check fixt req'd) | 45
10 | 3D Machining Completed | 50 | 10 | Quality Loop # 1 Complete | 50
11 | Assembly # 2 Completed | 55 | 11 | Wire Cut Trim Sections Completed | 55
12 | Die Closed in Press / Spotting Completed | 60 | 12 | Assembly of Trim Sections | 60
13 | First Panel to Gauge (Die Cut) (tryout mat'l / check fixt req'd) | 65 | 13 | First Part to Gauge (Die Cut) | 65
14 | Quality Loop # 1 Complete | 70 | 14 | Quality Loop # 1 Complete | 70
15 | Quality Loop # 2 Complete | 75 | 15 | Quality Loop # 2 Complete | 75
16 | Dimensionally Correct Part | 80 | 16 | Dimensionally Correct Part | 80
17 | Tryout Completed | 85 | 17 | Tryout Completed | 85
18 | Die Buyoff Complete at Die Shop | 90 | 18 | Die Buyoff Complete at Die Shop | 90
19 | Die at Homeline | 95 | 19 | Die at Homeline | 95
20 | Die Commissioned & Bought off at Home Line | 100 | 20 | Die Commissioned & Bought off at Home Line | 100

## TASKs -Weld %'s
# | Weld Cell % Complete | %
1 | Weld Cell Design Layout Complete | 5
2 | Long Lead Items Ordered | 15
3 | Weld Cell Started (Floor laid out and fencing started) | 20
4 | Geo Stations & Robots Complete and in place | 30
5 | Pipe and Wire Complete | 40
6 | Power On | 50
7 | Controls Hardware / Network Debug | 60
8 | Verify Weld Tools in Manual/Teach mode (Tooling 101) | 70
9 | Weld Verification (Started, Stepper programs in place) | 80
10 | Cells Run in Auto | 95
11 | Cells Run in Auto with Metal | 100

## APQP Open Issues Tracking
APQP Open Issues
Supplier/Mfg Location: |  |  |  |  | Part Number(s):
Duns Number: |  |  |  |  | Part Name:
Supplier Contact: |  |  |  |  | Program(s):
GM SQE Contact:
*Type Key: | S = Design-Supplier |  | T = Tooling | M = Manufacturing/Process |  | R = Production Control
| G = Design-GM |  | C = Capacity | O = Other __________________________
| F = Facilities |  | L = Late Release | P = Purchasing
Issue No. | Issue Date | Severity | Issues Description and/or Sketch | Person Responsible (Name) | Sketch | Action Plan & Progress to Plan | Forecast Completion Date | Status | Impact on PPAP and R@R
1
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
Reviewed by __________________Date __________ __________
Status Key:
25% Issue Identified
50% Action Plan Proposed
75% Action Plan Implemented
100% Issue Resolved
Severity:
1 - Director Support
2 - Manager/Supervisor Support
3 - SQE Support